### State of Arkansas

## Consolidated Annual Performance

## and Evaluation Report

Reporting period:

July 1, 2018 through June 30, 2019

Arkansas Economic Development Commission

Arkansas Development Finance Authority

Arkansas Department of Human Services

Arkansas Department of Health

Table of Contents

2018 Consolidated Annual Performance and Evaluation Report

Section                      									Page

CR-05 – Goals and Outcomes						 	    3

CR-10 – Racial and Ethnic composition of families assisted			  12

CR-15 – Resources and Investments						  13

CR-20 – Affordable Housing         						  19

CR-25 – Homeless and Other Special Needs					  21

CR-30 – Public Housing								  23

CR-35 – Other Actions								  24

CR-40 – Monitoring								  26

CR-45 – CDBG									  28

CR-50 – HOME									  29

CR-55 – HOPWA								  31

CR-56 – HFT									  33

CR-60 – ESG Subrecipients							  35

CR-65 – ESG Persons Assisted							  46

CR-70 – ESG Assistance Provided and Outcomes				  49

CR-75 – ESG Expenditures							  50

Attachments

Attachment 1:  State PER Financial Summary				         	  55

Attachment 2:  	PR-28 IDIS Activity Summary Report				113

Attachment 3:  	IDIS Matrix Codes 						119

Attachment 4:  PER Review Checklist						125

Attachment 5:  HOME Ethnic Data, CR-50, and County Designations		131

## CR-05 - Goals and Outcomes

Progress the jurisdiction has made in carrying out its strategic plan and its action plan.  91.520(a)

This could be an overview that includes major initiatives and highlights that were proposed and executed throughout the program year.

The Consolidated Annual Performance and Evaluation Report (CAPER) provides data on the amount and use of housing and community development funds received from the U. S. Department of Housing and Urban Development (HUD) by the State of Arkansas during the program year, July 1, 2018 through June 30, 2019. The investment of housing and community development resources administered by the State of Arkansas is guided by the Five-Year Consolidated Plan published on May 15, 2015. The state develops and publishes an Annual Update to the Consolidated Plan for directing its federally funded housing and community development programs during the upcoming year, and each year the state publishes the CAPER for the preceding program year. The State’s Consolidated Plan Committee oversees the long range and annual planning process. The Consolidated Plan Agency Board consists of representatives of the Arkansas Economic Development Commission (AEDC), the Arkansas Development Finance Authority (ADFA), the Arkansas Department of Health (ADH), and Arkansas Department of Human Services (DHS).

For progress made by CDBG, see the narrative sections below Table 1.

Notes: Shelter Homeless (homelessness prevention), reflects the total homeless person assisted in day and overnight shelters.

Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives.  91.520(g)

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

| Goal | Category | Source / Amount | Indicator | Unit of Measure | Expected – Strategic Plan | Actual – Strategic Plan | Percent Complete | Expected – Program Year | Actual – Program Year | Percent Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Admin | Administration | CDBG: $ / HOPWA: $ / HOME: $ / ESG: $ / HTF: $300000 / Housing Trust Fund: $0 | Other | Other | 5 | 4 | 80.00% | 1 | 1 | 100.00% |
| CHDO | Affordable Housing | HOME: $ | Homeowner Housing Added | Household Housing Unit | 100 | 30 | 30.00% | 21 | 9 | 42.86% |
| Child Care | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 0 | 0 |  |  |  |  |
| CoC Cap | Homeless |  | Other | Other | 5 | 0 | 0.00% |  |  |  |
| Eco Dev | Non-Housing Community Development | CDBG: $ | Jobs created/retained | Jobs | 2500 | 903 | 36.00% | 500 | 0 | 0.00% |
| Fac/ Infra | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 25000 | 10824 | 43.30% | 5000 | 0 | 0.00% |
| Fire Prot | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 15000 | 26368 | 175.79% | 3000 | 430 | 14.33% |
| HOPWA Hsg Asst | Non-Homeless Special Needs | HOPWA: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 675 | 527 | 78.07% | 135 | 160 | 118.52% |
| HOPWA Sup Svs | Non-Homeless Special Needs | HOPWA: $ | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 1000 | 874 | 87.40% | 200 | 261 | 130.50% |
| Infra | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 10000 | 483 | 4.83% |  |  |  |
| Perm Hsg | Homeless | HTF: $5400000 | Rental units constructed | Household Housing Unit | 0 | 0 |  | 34 | 0 | 0.00% |
| Perm Hsg | Homeless | HTF: $5400000 | Other | Other | 1 | 0 | 0.00% |  |  |  |
| Prev | Homeless | ESG: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 20000 | 954 | 5.00% | 4000 | 0 | 0.00% |
| Prev | Homeless | ESG: $ | Homeless Person Overnight Shelter | Persons Assisted | 0 | 4130 | 0.00% | 3000 | 2753 | 91.77% |
| Prev | Homeless | ESG: $ | Homelessness Prevention | Persons Assisted | 20000 | 1634 | 8.00% | 4000 | 0 | 0.00% |
| Pub Hlth | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 5000 | 0 | 0.00% |  |  |  |
| Purc Asst | Affordable Housing | HOME: $ | Direct Financial Assistance to Homebuyers | Households Assisted | 1250 | 776 | 62.08% | 206 | 263 | 127.67% |
| Rehab/ Recons | Affordable Housing | HOME: $ | Homeowner Housing Rehabilitated | Household Housing Unit | 225 | 70 | 31.11% | 47 | 6 | 12.77% |
| Rent Hsg | Affordable Housing | HOME: $ | Rental units constructed | Household Housing Unit | 125 | 93 | 74.40% | 27 | 45 | 166.67% |
| Rent Rehab | Affordable Housing | HOME: $ | Rental units rehabilitated | Household Housing Unit | 125 | 129 | 103.20% | 27 | 74 | 274.07% |
| Shel | Homeless | ESG: $ | Homeless Person Overnight Shelter | Persons Assisted | 20000 | 0 | 0.00% | 4000 | 2753 | 68.83% |
| Shel | Homeless | ESG: $ | Homelessness Prevention | Persons Assisted | 79000 | 0 | 0.00% | 15800 | 0 | 0.00% |
| Sr Ctrs | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 15000 | 2529 | 16.86% | 0 | 0 | 0.00% |
| TBRA | Affordable Housing | HOME: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 1375 | 327 | 23.78% | 289 | 76 | 26.30% |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

Assess how the jurisdiction’s use of funds, particularly CDBG, addresses the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified.

The Strategic Plan for 2018 laid out the direction the state intended to take in the distribution of CDBG, HOME, ESG, HOPWA, and NHTF funding for five years. The priorities listed were determined through consultation with service providers and consideration of a community survey that was conducted in the development of the Consolidated Plan. Some of the activities included will be targeted to individual households who qualify for the programs according to their income status (individual benefit). Other programs are directed toward particular areas within Arkansas where the median incomes of the census tracts involved are below 80 percent of the area median income (area benefit).

It should be noted that many of the CDBG projects funded with 2018 program funds are still ongoing, and actual accomplishment may not yet be realized. Typically, the State documents accomplishment for CDBG activities when the projects are completed. Additionally, for years 2016, 2017, and 2018, the accomplishments for the Goals of Child Care, Public Health, and Senior Centers will be reported in the Goal of Facilities and Infrastructure. These Goals were combined starting in Program Year 2016. As such, the accomplishments for Child Care, Public Health, and Senior Centers represent the accomplishments only in 2015, so the state is likely to only meet a minimum of 20% of the goal for those categories.

The State's progress towards addressing the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified, is detailed throughout this document, and below, specifically as it relates to CDBG:

Economic Development (Eco Dev)

In Program Year 2018 the State of Arkansas will identify and fund projects which lead to employment opportunities for the citizens of Arkansas. The state will provide approximately $9,743,035 in 2018 to cities and counties to fund eligible economic development activities, primarily grants, for the improvement of public infrastructure related to the location or expansion of industry in the state, and to capitalize loans that benefit businesses and industries that are locating or expanding in Arkansas. These grants will provide job opportunities to an estimated 500 persons. At least 51% of all new jobs created or retained by these projects will be held by or made available to persons with household incomes below 80% of the area median income.

Actual Accomplishments

As of June 30, 2019 the state had committed to awarding three economic developments project for a total of $9,350,000. These projects will improve economic opportunities for approximately 400 Arkansans through the improved access to job opportunities. Approximately 51% of the new jobs created by these projects will be made available to persons of low- to moderate-income.

Grantee		Project Type		 	Grant Total	   	Jobs Created (Planned) Recommended:

Clark County		Eonomic Development		$8,750,000 		  350

Lawrence County	Street/Road			$300,000		    15

City of Marmaduke	Equipment Purchase		$300,000		    35

General Assistance for Public Facilities and Infrastructure (Fac/Infra) (Childcare) (Pub Hlth)

Within the Public and Community Facilities and Infrastructure Priority Need, CDBG funds will be utilized for public facilities and public works projects. Within this Program CDBG funds will be utilized for and will generally be made available under the LMI Area Benefit or LMI Limited Clientele or Presumed Benefit National Objective measures. Funds are awarded for: senior centers; child care centers; public health facilities; youth centers; accredited public libraries; removal of architectural barriers from city halls or county courthouses for accessibility; street, curb, gutter, sidewalk, or storm sewer; flood control and drainage; and, other public facility or infrastructure project determined to be a high priority, and not eligible to be funded under another CDBG program. For the 2018 Program Year, AEDC is considering funding public facility and public infrastructure projects with an anticipated $1,911,484 in CDBG resources. The award amount is based on beneficiary data of the project area as well as the feasibility and need for the project. An estimated 5,000 persons will benefit from these activities. Note that additional funds may be provided for this line item in the future through the de-obligation of unused funds from other line items, or from de-obligated funds from previous funding years.

Actual Accomplishments:

As of June 30, 2019 the state had awarded three grants and had made three commitments to projects totaling $1,172,092 to benefit an estimated 11,783 persons.

Grantee		   	 Project Type	      	Grant Total	Total Persons to be Served

Awarded: General Assistance Public Facilities & Infrastructure (3 Projects)

Lonoke County			Abused Children	$219,200.00  		    284

White County 			Abused Children	 $219,200.00 		    425

City of Batesville		Childcare	     	$143,700.00  	  	      92

Subtotal:				     		$582,100.00		  1001

Grantee		   	 Project Type	     	Grant Total	Total Persons to be Served

Committed: General Assistance Public Facilities & Infrastructure (3Projects)

City of Osceola		 	Community Center  	$163,492.00		  7,105

City of Corning 		 	Drainage	     	$208,000.00 		  3,225

City of Paragould		Homeless Shelter      	$218,500.00  	  	     452

Subtotal:				     		$589,992.00		 10782

Grand Totals (6 projects)			  	$1,172,092.00		11,783

Water/Wastewater (Infra)

For Program Year 2018, the State of Arkansas planned to enhance a suitable living environment for the citizens of Arkansas by providing improved access to clean, safe drinking water and safe sanitary sewer systems. In 2018, the state made available $4,428,653 in funding for the construction or expansion of water and wastewater projects. These improvements will provide assistance to an estimated 2,000 persons. At least 51% of all households benefiting from this line item will have incomes below 80% of the area median income.

Actual Accomplishments.

Grantee		   	 Grant Total	Total Persons to be Served

Funded: Infrastructure-Water/Wastewater (4 projects)

Benton County			$223,000.00		     37

City of Huntsville		$221,500.00		2,346

City of Eureka Springs		$221,500.00		2,073

City of Ward			$224,500.00		      39

Subtotal			$890,500.00		 4,495

Committed: Infrastructure-Water/Wastewater (10 projects)

City of Foreman 		$200,000.00		 1,011

City of Wynne			$221,500.00		     166

City of Magnolia		$200,000.00		11,577

City of Prescott			$199,987.00		  3,296

City of DeQueen		$200,000.00		  6,594

Town of Louann			$200,000.00		     164

Calhoun County			$793,390.00		        52

City of Ogden			$166,000.00		      180

City of Reyno			$215,500.00		      456

City of Caraway			$216,000.00		   1,220

Subtotal			$2,612,377.00		 24,716

Grand Totals (9 records	)	$3,502,877.00		 29,211

Fire Protection and Community Centers for Rural Communities (Fire Prot)

In Program Year 2018, the State of Arkansas, in partnership with the AEDC Division of Rural Services, planned to provide $1,000,000 to fund the construction, expansion or renovation of Community Centers and Fire Stations or Multi-Purpose Centers, and for the purchase of fire trucks and fire protection equipment in cities and unincorporated rural areas with a population of less than 3,000 persons.  These centers will provide meeting areas and will provide enhanced fire protection to an estimated 3,000 persons, more than 51% of whom will have incomes below 80% of the area median-income.

Actual Accomplishments:

As of June 30, 2019, the State had executed 15 grant agreements for fire protection projects and community center projects totaling $996,958.66. These projects will enhance a suitable living environment for approximately 11,807 rural Arkansans through the improved access to Community Centers, and through the availability of affordable fire protection services.

Grantee		   	 Project Type 		Grant Total	Total Persons to be Served

Program Type: Fire Protection and Community Centers (15 projects)

Town Of Allport		 	Community Center	$75,000.00	   	       228

City Of Dover		  	Community Center	$75,000.00		     2288

Town Of South Lead Hill	  	Community Center	$60,668.00		       102

Town Of Minneral Springs	Fire Protection		$75,000.00		     1208

Greene County		  	Fire Protection	  	$75,000.00		     3650

White County		  	Fire Protection 		$57,628.00		       355

City Of Winthrop		Fire Protection		$75,000.00		       152

Town of Oxford 		Fire Protection   	$46,766.00		       670

Logan County 		  	Fire Protection		$60,000.00		     3296

City Of Elaine			Fire Protection		$72,779.00		       636

City Of Gould			Fire Protection		$75,000.00		       837

Town Of Lynn		  	Fire Protection		$31,005.00		         96

Town Of Lexa		 	Fire Protection		$69,962.66		       286

City of Mountainburg	 	Fire Protection		$73,150.00		       530

City of Summitt	 	 	Fire Protection		$75,000.00		       430

Grand Totals (15 records)			            $996,958.66		    7,083

## CR-10 - Racial and Ethnic composition of families assisted

Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)

|  | CDBG | HOME | HOPWA | ESG | HTF |
| --- | --- | --- | --- | --- | --- |
| White | 1,167 | 444 | 0 | 0 | 0 |
| Black or African American | 44 | 350 | 0 | 0 | 0 |
| Asian | 7 | 10 | 0 | 0 | 0 |
| American Indian or American Native | 10 | 4 | 0 | 0 | 0 |
| Native Hawaiian or Other Pacific Islander | 6 | 7 | 0 | 0 | 0 |

| Total | 1,234 | 815 | 0 | 0 | 0 |
| --- | --- | --- | --- | --- | --- |

| Hispanic | 91 | 95 | 0 | 0 | 0 |
| --- | --- | --- | --- | --- | --- |
| Not Hispanic | 1,143 | 720 | 0 | 0 | 0 |

Table 2 – Table of assistance to racial and ethnic populations by source of funds

Narrative

Additional HOME data is included in the Table of Assistance to Racial and Ethnic Status. See Attachment 5.

The following represents the proposed racial and ethnicity status of persons expected to benefit from CDBG, and the racial and ethnicity status of persons benefitting from completed CDBG projects in 2018:

## CR-15 - Resources and Investments 91.520(a)

Identify the resources made available

| Source of Funds | Source | Resources Made Available | Amount Expended During Program Year |
| --- | --- | --- | --- |
| CDBG | public - federal | 19,714,610 | 438,940 |
| HOME | public - federal | 10,207,827 | 6,228,397 |
| HOPWA | public - federal | 1,488,875 | 718,861 |
| ESG | public - federal | 2,694,846 |  |
| HTF | public - federal | 9,000,000 | 5,357 |

Table 3 - Resources Made Available

Narrative

Community Development Block Grant (CDBG) program funding levels were consistent with anticipated amounts. Program income was estimated to be $2,000,000. Program income was actually $1,360,662.92 as of June 30, 2019.

This amount was added to the Arkansas Economic Development Commission budget for the 2018 allocation.

Arkansas Development Finance Authority (ADFA) - HOME Investment Partnerships Program (HOME) received $10,207,827 as its FY 2018 HOME allocation. Program income on hand at the end of FY 2018 was estimated to be $4,278,799 from HOME funded activities. The actual amount of program income received during the reporting period was $4,989,178 which includes Recaptured Homebuyer and Ineligible Use Funds. The increase in program income was due additional loan repayments and loan payoffs. According to the PR 07 (HOME Drawdown Report by Voucher Number), HOME funds expended during FY 2018 was $6,228,397. This amount includes program income and funds committed and expended from prior years.

ADFA-National Housing Trust Fund (NHTF) was awarded $3,000,000 in 2017 and an additional $3,000,000 in 2018 from HUD’s NHTF for the construction of rental housing for Arkansas’ extremely low income veterans.  Our goal is to construct approximately 34 units/homes with these funds. On July 18, 2018, ADFA published NHTF NOFA of $6,000,000 on our website at https://adfa.arkansas.gov/files/.  NOFA applications may be emailed to nofa@adfa.arkansas.gov through 10/15/18.  After that, the applications will be underwritten and scored by ADFA.  Pending ADFA’s Board approval, the awards will be announced.  For Fiscal Year 2018 (7/1/18 through 6/30/19), ADFA has drawn down administrative costs of $13,794.00 from IDIS.

Emergency Solutions Grants (ESG) funding levels were consistent with anticipated amounts. ESG amount expended is an estimate on funds that have been drawn down as of June 2019.

Housing Opportunities for Persons with AIDS (HOPWA) funding was 106.34% higher than planned amounts (primarily due to additional funding sourced from prior HUD funds released for use from FY 13, and 14 as well as FY 16 and FY 17 allocations still within the 3-year spending window).

Note: Under Resources Made Available: This amount includes unexpended funds from prior FY HUD allocations in addition to FY 2018 HUD allocation for HOPWA.

Identify the geographic distribution and location of investments

| Target Area | Planned Percentage of Allocation | Actual Percentage of Allocation | Narrative Description |
| --- | --- | --- | --- |
| CDBG Eligible Areas | 17 | 17 | Low-Income Areas for Area Benefit |
| Statewide | 83 | 83 | Areas for Individual Benefit and Administration |

Table 4 – Identify the geographic distribution and location of investments

Narrative

Projects created in response to the five federal funding programs, CDBG, HOME, HOPWA, ESG and NHTF, are spread across non-entitlement communities throughout the state. The vast majority of the combined funding is provided through individual benefit criteria, available to low-income individuals/households regardless of the demographics of the community in which they reside. A smaller portion, primarily funded through the CDBG Program, addresses infrastructure and public facility concerns within CDBG eligible areas where more than 51 percent of residents earn less than 80 percent of the area median income. For CDBG, 50 percent of CDBG funding will be used in CDBG area benefit eligible areas.

Investments are allocated according to responses to programmatic opportunities and client response to funding availability. Rehab programs may be targeted to the CDBG Eligible Areas or as individual benefit to low-income households. Public services, likewise, may be offered in low-income areas or generally to all qualified residents.  Public facilities and infrastructure projects are restricted to CDBG Eligible Areas only.

The proposed allocation of funds was based on federal funding requirements for each formula-allocated grant. Areas of low- to moderate-income concentration and certain areas of high minority concentration are targeted. Areas of low homeownership and deteriorating housing conditions were also considered in the targeting process.

The distribution of funds by target area is projected to be primarily Statewide due to use of funds for administrative, non-profit support, and individual benefit-oriented programmatic uses of the funds. The remaining funds are estimated to be spread through smaller CDBG-eligible areas.

Higher ratings were given to counties with racial and low-income concentrations; and housing resource agencies were encouraged to develop more affordable housing resources in counties with proportionately less subsidized rental housing.

Leveraging

Explain how federal funds  leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.

Match liability amount is based on IDIS PR 33 report as of August 12, 2019.

| Fiscal Year Summary – HOME Match |  |
| --- | --- |
| 1. Excess match from prior Federal fiscal year | 2,831,288 |
| 2. Match contributed during current Federal fiscal year | 791,088 |
| 3. Total match available for current Federal fiscal year (Line 1 plus Line 2) | 3,622,376 |
| 4. Match liability for current Federal fiscal year | 878,106 |
| 5. Excess match carried over to next Federal fiscal year (Line 3 minus Line 4) | 2,744,270 |

Table 5 – Fiscal Year Summary - HOME Match Report

| Match Contribution for the Federal Fiscal Year |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project No. or Other ID | Date of Contribution | Cash (non-Federal sources) | Foregone Taxes, Fees, Charges | Appraised Land/Real Property | Required Infrastructure | Site Preparation, Construction Materials, Donated labor | Bond Financing | Total Match |
| 2015-29 | 03/26/2019 | 10,340 | 0 | 0 | 0 | 0 | 0 | 10,340 |
| 2015-38 | 12/11/2018 | 0 | 70,000 | 0 | 0 | 0 | 0 | 70,000 |
| 2015-40 | 12/13/2018 | 0 | 31,250 | 0 | 0 | 0 | 0 | 31,250 |
| 2015-42 | 12/11/2018 | 0 | 70,000 | 0 | 0 | 0 | 0 | 70,000 |
| 2015-44 | 10/19/2018 | 0 | 55,202 | 0 | 0 | 10,000 | 0 | 65,202 |
| 2016-13 | 05/08/2019 | 0 | 0 | 0 | 0 | 3,804 | 0 | 3,804 |
| 2016-17 | 05/22/2019 | 0 | 211,000 | 0 | 0 | 0 | 0 | 211,000 |
| 2017-17 | 06/06/2019 | 240,000 | 0 | 0 | 0 | 0 | 0 | 240,000 |
| 2017-20 | 12/17/2018 | 0 | 9,009 | 0 | 0 | 366 | 0 | 9,375 |
| 2017-24 | 03/26/2019 | 0 | 10,117 | 0 | 0 | 0 | 0 | 10,117 |

Table 6 – Match Contribution for the Federal Fiscal Year

HOME MBE/WBE report

| Program Income – Enter the program amounts for the reporting period |  |  |  |  |
| --- | --- | --- | --- | --- |
| Balance on hand at beginning of reporting period $ | Amount received during reporting period $ | Total amount expended during reporting period $ | Amount expended for TBRA $ | Balance on hand at end of reporting period $ |
| 2,483,322 | 6,113,444 | 2,487,123 | 0 | 6,109,653 |

Table 7 – Program Income

Minority Business Enterprises and Women Business Enterprises – Indicate the number and dollar value of contracts for HOME projects completed during the reporting period

|  | Total | Minority Business Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |

| Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Dollar Amount | 9,209,206 | 0 | 0 | 0 | 0 | 9,209,206 |
| Number | 39 | 0 | 0 | 0 | 0 | 39 |

| Sub-Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number | 30 | 0 | 0 | 2 | 5 | 23 |
| Dollar Amount | 3,884,959 | 0 | 0 | 268,800 | 1,118,804 | 2,497,355 |

|  | Total | Women Business Enterprises | Male |
| --- | --- | --- | --- |

| Contracts |  |  |  |
| --- | --- | --- | --- |
| Dollar Amount | 1,209,578 | 0 | 1,209,578 |
| Number | 13 | 0 | 13 |

| Sub-Contracts |  |  |  |
| --- | --- | --- | --- |
| Number | 17 | 0 | 17 |
| Dollar Amount | 1,209,578 | 0 | 1,209,578 |

Table 8 - Minority Business and Women Business Enterprises

Minority Owners of Rental Property – Indicate the number of HOME assisted rental property owners and the total amount of HOME funds in these rental properties assisted

|  | Total | Minority Property Owners |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

Table 9 – Minority Owners of Rental Property

Relocation and Real Property Acquisition – Indicate the number of persons displaced, the cost of relocation payments, the number of parcels acquired, and the cost of acquisition

|  | Number | Cost |
| --- | --- | --- |
| Parcels Acquired | 0 | 0 |
| Businesses Displaced | 0 | 0 |
| Nonprofit Organizations Displaced | 0 | 0 |
| Households Temporarily Relocated, not Displaced | 0 | 0 |

| Households Displaced | Total | Minority Property Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Cost | 0 | 0 | 0 | 0 | 0 | 0 |

Table 10 – Relocation and Real Property Acquisition

## CR-20 - Affordable Housing 91.520(b)

Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of Homeless households to be provided affordable housing units | 0 | 0 |
| Number of Non-Homeless households to be provided affordable housing units | 0 | 0 |
| Number of Special-Needs households to be provided affordable housing units | 0 | 0 |
| Total | 0 | 0 |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through Rental Assistance | 289 | 76 |
| Number of households supported through The Production of New Units | 27 | 45 |
| Number of households supported through Rehab of Existing Units | 74 | 74 |
| Number of households supported through Acquisition of Existing Units | 263 | 206 |
| Total | 653 | 401 |

Table 12 – Number of Households Supported

Discuss the difference between goals and outcomes and problems encountered in meeting these goals.

The outcomes reported above are based on activities that were completed in the HUD Integrated Disbursement and Information System (IDIS) during this reporting period. The one-year goals set for HOME funded programs are based on available resources and funding commitments. A reduction in actual outcome was due to providing technical support to new recipients, changes within their organizations, funded projects with delays in construction and/or a reduction in funding priorities during the reporting period. ADFA is working diligently with sub-recipients to make sure these projects move forward.

Discuss how these outcomes will impact future annual action plans.

Future annual action plans will continue to consider funding priorities based on housing needs. The state will continue monitoring the progress of projects that have been funded but not closed, as well as, projects that are underway but delayed due to various plausible reasons. The state will continue to monitor the housing needs in underserved areas as well as developer's subsidy and down payment and closing cost assistance. Additionally, the State will monitor lower interest rates to encourage homeownership for low- to moderate-income households.

Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.

| Number of Households Served | CDBG Actual | HOME Actual | HTF Actual |
| --- | --- | --- | --- |
| Extremely Low-income | 0 | 70 | 0 |
| Low-income | 0 | 382 |  |
| Moderate-income | 0 | 0 |  |
| Total | 0 | 452 | 0 |

Table 13 – Number of Households Served

Narrative Information

The above numbers are from the PR 23 report in the HUD Integrated Disbursement and Information System (IDIS) during this reporting period.

*Demographic information is not available for ten (10) rental rehabilitation units that are vacant.

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:

Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs

DHS/DCO provided funding to eligible agencies throughout the state. The funds were used to establish relationships with unsheltered homeless people by providing food and water, basic hygienic items, and rain cloaks. Individual needs were assessed where these interactions occurred. This activity supported the state’s goal of moving unsheltered homeless into safer nighttime sleeping place by increasing levels of trust between unsheltered homeless, who often have mental health issues, and local agencies who are able to assist with housing needs.

Addressing the emergency shelter and transitional housing needs of homeless persons

DHS/DCO provided funding to eligible agencies throughout the state. The funds were used to address the operational needs of facilities that provide emergency shelter to literally homeless individuals, families, women with children, and to those fleeing domestic violence or other unsafe situations. In addition to safe nighttime places to sleep, the sub-grant recipients also provided essential services such as budgeting, basic life skills, and assistance with connecting the program participants to sources of income. $160,000 went into a multimillion-dollar project to renovate an empty commercial building into an emergency shelter complex that will serve the needs of low income area residents as well as homeless persons.

Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are:  likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions);  and,  receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs

DHS/DCO provided funding to eligible agencies throughout the state. The funds were used to prevent low-income persons and families from becoming homeless by providing financial assistance with rent payments to those about to be evicted from their FMR- and rent reasonableness-compliant residences. These funds also assisted in transitioning participants from correctional institutions into suitable housing. These activities supported the State’s goal of eliminating homelessness by preventing individuals and families at risk of homelessness from becoming actually homeless.

Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again

DHS/DCO provided funding to eligible agencies throughout the state. The funds were used to assist homeless persons and families, and those fleeing domestic violence or other unsafe living situations, with obtaining safe, affordable FMR- and rent reasonableness-compliant residences. These funds were primarily used to assist participants who were transitioning from emergency shelters and had already received supportive services such as job training, budgeting skills training, and/or assistance with connecting to mainstream assistance programs. These activities supported the State’s goal of eliminating homelessness by moving participants from temporary housing in shelters to permanent housing.

## CR-30 - Public Housing 91.220(h); 91.320(j)

Actions taken to address the needs of public housing

ADFA continues to fund Tenant-Based Rental Assistance (TBRA) to public housing authorities to supplement their Section 8 vouchers and to agencies in communities that lack rental assistance to address the housing cost burden.

Actions taken to encourage public housing residents to become more involved in management and participate in homeownership

ADFA does not manage public housing authorities (PHA) units.

Actions taken to provide assistance to troubled PHAs

ADFA does not manage public housing authorities (PHA) units.

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i)

There are no known public policy barriers to affordable housing development in Arkansas, though market factors do influence the ability to produce a range of housing to address all income levels. Most of these factors, including the cost of construction, price of developable land, and tenant/homebuyer incomes, are beyond the influence of the State of Arkansas. Where possible, the state provides or funds services that address market factors, such as job training and business development activities.

Actions taken to address obstacles to meeting underserved needs.  91.220(k); 91.320(j)

The state will continue to look for new funding sources for programs to address underserved needs. Funding is the major obstacle in providing the services needed to focus on the vast variety of issues that prevent families from breaking out of poverty and from living in the best, most affordable housing possible.

Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)

ADFA requires dwelling units built prior to 1978 comply with the rehabilitation requirements of the Lead Safe Housing Rule (24 CFR Part 35, Subpart J).

The requirements of the Lead Safe Housing Rule depend on the level of assistance provided to the unit. The summary below provides a brief overview of the regulations.

For units with a level of assistance less than $5,000, paint testing must be conducted on all painted surfaces to be disturbed or replaced during the renovation, or it must be presumed that all these painted surfaces are coated with lead-based paint. Safe work practices must be employed during the rehabilitation work, and upon completion, a clearance examination of the worksite is required. Clearance of the worksite is required prior to the unit being reoccupied.

For units with a level of assistance over $5,000 and up to $25,000, lead hazards must be identified by a risk assessment (or presumed to be present) and then addressed through interim controls or standard treatments. Proper safe work practices, trained staff, and unit clearance are also required.

For units with a level of assistance over $25,000, lead hazards must be identified through a risk assessment (or presumed to be present) and addressed through abatement by a certified abatement contractor. Clearance is required.

All homeowners must receive the lead-based based pamphlet, Protect Your Family From Lead in Your Home as well as other relevant information pertaining to the rehabilitation work. The Recipients must have documented evidence that this notice was provided.

Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)

The state continues its efforts in conjunction with the seven Continua of Care in Arkansas to reduce the number of poverty-level families through the development of services needed to assist those families with educational opportunities, job growth, and life skills training through the various social service agencies operating in the communities across the state.

Actions taken to develop institutional structure. 91.220(k); 91.320(j)

- Worked with non-profit organizations to address community needs and provide support to federal and non-federal funding initiatives.

- Worked with private industry to address important issues that hamper housing and community development efforts.

- Identified opportunities to create private/public partnerships for project finance and development to leverage federal funds.

Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)

The state continues to coordinate planning activities with subgrantees and private housing and social service agencies, including participation in the Balance of State Continuum of Care meetings, development of the Continuum of Care, and coordinate the enumeration of point-in-time and homeless surveys by continua throughout the state. State staff will also continue its participation in other coalitions and study groups as the opportunity arises.

Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice.  91.520(a)

As part of the efforts to address impediments identified in the State’s Analysis of Impediments, the Arkansas Fair Housing Commission was identified to develop education materials to increase public awareness of fair housing issues. The Arkansas Fair Housing Commission publishes a brochure explaining fair housing, including mortgage violations, housing violations, and the complaint process. The information published by the Arkansas Fair Housing Commission is also accessible via their website at www.arkansasfairhousing.com. ADFA has a Memorandum of Understanding (MOU) with the Arkansas Fair Housing Commission to develop and conduct workshops that will introduce participants to the key aspects of the Fair Housing Act and ANSI design standards; applicable ADA requirements; an overview of federal and state fair housing laws; reasonable accommodations and modifications; and compliance. ADFA requires participants applying for HOME Program funds to successfully complete the Fair Housing Training Course prior to receiving funds.

## CR-40 - Monitoring 91.220 and 91.230

Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements

Citizen Participation Plan 91.105(d); 91.115(d)

Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports.

The Citizen Participation Plan (CPP) is the CPP established for the State of Arkansas’s Five-year Consolidated Plan, which covers the 2015 through 2019 Program Years.

Notification and Comment Period

In accordance with the state’s CPP, the state provided the public with advance notice of the availability of the draft version of the Consolidated Annual Performance and Evaluation Report (CAPER), how the document could be obtained, and the time frame during which it would be available.

Notification

A legal advertisement was published on September 8, 2019, in The Arkansas Democrat-Gazette, a newspaper of general circulation in Arkansas. The notice indicated when the document would be available and provided: a web address to download a copy of the report, a physical address where a hard copy of the report could be reviewed and a phone number and email address for requesting copies to be mailed or emailed.  Per the state’s CPP, additional avenues for public notification were also used to capitalize on new technology and expand the reach of the notification effort.  The draft document was made available via download from the www.arkansasedc.com/grants website, at each of the partner agency offices during normal business hours and via email from the Arkansas Economic Development Commission, lead agency for the development of the CAPER.

Timeframe for review and comment

The 15-day period for public review and comment ran from September 8 through September 23, 2019. The deadline for submitting written comments was close of business at the end of the 15-day period, or 4:30 pm on September 23rd.

Summary of Comments Received

No comments were received during this time.

Proof of Publication

## CR-45 - CDBG 91.520(c)

Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.

In 2018, the state changed its method of distribution for CDBG to end the referral process through which partner agencies undertook a pre-application process and then made referrals to AEDC for projects which should be invited to formally apply.
   
Projects like senior centers, child care centers, and public health units were scored competitively under the General Assistance set-aside. The state will define ways to commit funds to community and economic development projects in order to spend funds in a timely manner during the current funding year and future allocation years. As of June 30, 2018, 100% of the CDBG allocation was obligated to projects which primarily benefit low- to moderate-income persons.

Changes in the State CDBG program objectives or sub-goals are described in the 2015-2019 Consolidated Plan and 2018 Annual Action Plan. Programmatic changes are also discussed in the Plans.

In 2018, the State intends to allow water and wastewater projects to be submitted through the General Assistance set-aside. As of July 1, 2018, the Arkansas Economic Development Commission and the Arkansas Natural Resources Commission (ANRC) terminated a memorandum of understanding under which ANRC selected and administered water and wastewater projects funded with CDBG. In 2018 and going forward, AEDC will select and administer them along with all other CDBG projects.

Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?

No

[BEDI grantees]  Describe accomplishments and program outcomes during the last year.

N/A

## CR-50 - HOME 91.520(d)

Include the results of on-site inspections of affordable rental housing assisted under the program to determine compliance with housing codes and other applicable regulations

Please list those projects that should have been inspected on-site this program year based upon the schedule in §92.504(d). Indicate which of these were inspected and a summary of issues that were detected during the inspection. For those that were not inspected, please indicate the reason and how you will remedy the situation.

See Attachment 5 - CR50-Unit Inspections

Provide an assessment of the jurisdiction's affirmative marketing actions for HOME units. 92.351(b)

To further the commitment to nondiscrimination and equal opportunity in housing, and in accordance with the regulations of the HOME Investment Partnerships Program (HOME), ADFA requires HOME subgrantees, Community Housing Development Organizations (CHDOs), and developers of HOME Program funds to comply with the affirmative marketing requirements.  Applicants applying for HOME funds must submit an affirmative marketing plan upon application and adopt policies and procedures that inform the public, potential tenants, homebuyers, homeowners and rental property owners of their program through an Affirmative Marketing Plan (AMP or Plan).

Refer to IDIS reports to describe the amount and use of program income for projects, including the number of projects and owner and tenant characteristics

Total program income available for FY 2018 was $4,989,179 which includes recaptured homebuyer funds of $58,571 and ineligible use funds of $89,064.  Ten percent of ordinary program income

($141,714) was retained for administration which excludes recaptured homebuyer and ineligible use funds. Program income was used for various projects as requests for drawdowns were submitted and processed.

Describe other actions taken to foster and maintain affordable housing.  91.220(k) (STATES ONLY: Including the coordination of LIHTC with the development of affordable housing).  91.320(j)

Low-income Housing Tax Credit Program (LIHTC)

The Arkansas Development Finance Authority (ADFA) administers the federal Low-income Housing Tax Credit Program (LIHTC) for the State. The program incentivizes private equity investments from owners and developers to build or rehabilitate multi-family housing that is rented to families whose income is not greater than 60% of the area median. Developers receiving tax credits sell them to corporations that use them to offset federal income tax liability. For calendar year 2018, ADFA authorized credits totaling $7,476,821 creating 543 affordable, safe, decent apartments for low-income families.

Single-Family Homeownership Program

ADFA utilizes Mortgage-Backed Securities (MBS) sold on the open market to generate funds for the single-family homeownership program.  Loans are originated by participating lenders throughout the state to homebuyers.  During FY 2018, ADFA made 548 MBS loans totaling $104,300,315 with an average loan amount of $126,886.

Mortgage Credit Certificate (MCC) Program

The Mortgage Credit Certificate (MCC) Program provides for a federal tax credit of up to $2,000 per year as long as the home is used as the borrower’s primary residence.  The MCC is an incentive for first-time homebuyers to purchase a home. During FY 2018, ADFA issued 571 Mortgage Credit Certificates totaling $67,778,470 with an average loan amount of $118,701.

## CR-55 - HOPWA 91.520(e)

Identify the number of individuals assisted and the types of assistance provided

Table for report on the one-year goals for the number of households provided housing through the use of HOPWA activities for: short-term rent, mortgage, and utility assistance payments to prevent homelessness of the individual or family; tenant-based rental assistance; and units provided in housing facilities developed, leased, or operated with HOPWA funds.

| Number of Households Served Through: | One-year Goal | Actual |
| --- | --- | --- |
| Short-term rent, mortgage, and utility assistance to prevent homelessness of the individual or family | 75 | 56 |
| Tenant-based rental assistance | 60 | 104 |
| Units provided in permanent housing facilities developed, leased, or operated with HOPWA funds | 0 | 0 |
| Units provided in transitional short-term housing facilities developed, leased, or operated with HOPWA funds | 0 | 0 |
| Total | 135 | 160 |

Table 14 – HOPWA Number of Households Served

Narrative

Goal 1: Provide direct housing subsidy assistance to enable low-income, HIV-positive individuals to remain in their homes and to reduce their risks of homelessness.

Objective 1: Provide tenant-based rental assistance (TBRA).

Outcome: Housing stability.

Outcome Statement: Establish and/or better maintain a stable living environment in housing that is safe, decent, affordable, and sanitary.

Performance Indicator: Provide funding to maintain or increase assistance to 60 households utilizing tenant-based rental assistance(TBRA) for a period of up to 36 months.

Actual accomplishments: HOPWA expended $407,833.00 to maintain or increase assistance to one hundred four (104) households utilizing tenant-based rental assistance (TBRA) for a period of 12 months out of a 36-month eligibility period. This was 44 more than projected in the FY 2018 annual plan.

Objective 2:  Provide short-term rent, mortgage, and utility assistance (STRMU).

Outcome:  Housing stability.

Outcome Statement: Establish and/or better maintain a stable living environment in housing that is safe, decent, affordable, and sanitary.

Performance Indicator: Provide funding to maintain or increase assistance to 75 households accessing short-term rent, mortgage, and utility assistance (STRMU) for some portion of the permitted 21-week period.

Actual Accomplishments: HOPWA expended $92,919.00 to maintain or increase assistance to fifty-six (56) households accessing short-term rent, mortgage, and utility assistance (STRMU) for some portion of the permitted 21-week period. This was 19 less than projected in the FY 2018 annual plan.

## CR-56 - HTF 91.520(h)

Describe the extent to which the grantee complied with its approved HTF allocation plan and the requirements of 24 CFR part 93.

The state is implementing the approved NHTF Allocation Plan, which requires that all NHTF-funded activities be reserved for extremely low-income (ELI) households, which are those at or below 30% of area median income (AMI). Per 24 CFR 93.250(a), in any fiscal year in which the total amount available for allocation of HTF funds is less than $1 billion, ADFA will use 100% of its HTF grant for the benefit of ELI families or families with incomes at or below the poverty line (whichever is greater).

Arkansas Development Finance Authority (ADFA) in its role as the designated administrator of NHTF funds for the State of Arkansas (State), will use the annual grant for new construction rental housing and will use up to ten (10) percent of each annual grant for the grantee’s reasonable administrative and planning costs. All NHTF-assisted rental housing must meet a minimum affordability period of 30 years.

ADFA will administer the NHTF program to provide funds to develop new construction of decent, safe, and sanitary rental housing, primarily targeting a specific underserved group: The ELI Veteran population in Arkansas.

Regarding progress, ADFA awarded $1,058,925 for 9 Single Family New Construction rentals which will benefit ELI Veteran households. Funding was awarded in the spring of 2019 and it is expected construction will begin in the spring of 2020.

Compliance with the requirements of 24 CFR part 93

Recipients of NHTF funding are required to determine that each family occupying a NHTF-funded unit is income-eligible as required by 24 CFR 93.151, and income targeting requirements described in 24 CFR 93.250 will be met regardless of the annual allocation for HTF funds as all occupants of the NHTF-funded units are required to be at or below 30% AMI or the federal poverty level, whichever is greater.

The only eligible activity for the state’s HTF program is new rental housing. This is in compliance with the HTF eligible activities provided for in 24 CFR 93.200 and further ADFA’s NHTF program does not allow for prohibited activities identified in 24 CFR 93.204. In selecting projects for funding, ADFA ensure that sites for the proposed new construction meet requirements in 24 CFR 983.57(e)(2). Per requirements established in 24 CFR 93, ADFA will follow established policies and procedures. These include: eligibility as affordable rental housing, maximum per unit development subsidy amount, underwriting, subsidy layering, property standards, tenant protections and selection, other applicable Federal requirements, and performance reviews and sanctions. Some of these are described in the Method of Distribution and NHTF program specific sections of the Annual Action Plan along with program documents on ADFA’s website.

| Tenure Type | 0 – 30% AMI | 0% of 30+ to poverty line (when poverty line is higher than 30% AMI) | % of the higher of 30+ AMI or poverty line to 50% AMI | Total Occupied Units | Units Completed, Not Occupied | Total Completed Units |
| --- | --- | --- | --- | --- | --- | --- |
| Rental | 0 | 0 | 0 | 0 | 0 | 0 |
| Homebuyer | 0 | 0 | 0 | 0 | 0 | 0 |

Table 15 - CR-56 HTF Units in HTF activities completed during the period

## CR-60 - ESG 91.520(g) (ESG Recipients only)

ESG Supplement to the CAPER in e-snaps

For Paperwork Reduction Act

1. Recipient Information—All Recipients Complete

Basic Grant Information

| Recipient Name | ARKANSAS |
| --- | --- |

| Organizational DUNS Number | 024720901 |
| --- | --- |

| EIN/TIN Number | 710847443 |
| --- | --- |

| Indentify the Field Office | LITTLE ROCK |
| --- | --- |

| Identify CoC(s) in which the recipient or subrecipient(s) will provide ESG assistance |  |
| --- | --- |

ESG Contact Name

| Prefix | Ms |
| --- | --- |

| First Name | Lorie |
| --- | --- |

| Middle Name | 0 |
| --- | --- |

| Last Name | Williams |
| --- | --- |

| Suffix | 0 |
| --- | --- |

| Title | Assistant Director |
| --- | --- |

ESG Contact Address

| Street Address 1 | PO Box 1437, S 330 |
| --- | --- |

| Street Address 2 | 0 |
| --- | --- |

| City | Little Rock |
| --- | --- |

| State | AR |
| --- | --- |

| ZIP Code | - |
| --- | --- |

| Phone Number | 5016828714 |
| --- | --- |

| Extension | 0 |
| --- | --- |

| Fax Number | 5016826736 |
| --- | --- |

| Email Address | lorie.williams@dhs.arkansas.gov |
| --- | --- |

ESG Secondary Contact

| Prefix | Mrs |
| --- | --- |

| First Name | Mary |
| --- | --- |

| Last Name | Franklin |
| --- | --- |

| Suffix | 0 |
| --- | --- |

| Title | Director, Division of County Operations |
| --- | --- |

| Phone Number | 5016828377 |
| --- | --- |

| Extension | 0 |
| --- | --- |

| Email Address | Mary.Franklin@dhs.arkansas.gov |
| --- | --- |

2. Reporting Period—All Recipients Complete

| Program Year Start Date | 07/01/2018 |
| --- | --- |

| Program Year End Date | 06/30/2019 |
| --- | --- |

3a. Subrecipient Form – Complete one form for each subrecipient

Subrecipient or Contractor Name: CROWLEY'S RIDGE DEVELOPMENT COUNCIL, INC City: Jonesboro State: AR Zip Code: 72401, 8139 DUNS Number: 097906705 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $26,400

Subrecipient or Contractor Name: COMMUNITY ACTION PROGRAM FOR CENTRAL ARKANSAS City: Conway State: AR Zip Code: 72034, 6517 DUNS Number: 164572000 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $179,900

Subrecipient or Contractor Name: NEXT STEP DAY ROOM, INC. City: Fort Smith State: AR Zip Code: 72901, 2103 DUNS Number: 807060751 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $21,400

Subrecipient or Contractor Name: 7HILLS HOMELESS CENTER City: Fayetteville State: AR Zip Code: 72701, 7151 DUNS Number: 091443510 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $131,400

Subrecipient or Contractor Name: THE SALVATION ARMY-TEXARKANA City: Texarkana State: AR Zip Code: 71854, 6017 DUNS Number: 124154969 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $99,900

Subrecipient or Contractor Name: BETTER COMMUNITY DEVELOPMENT, INC. City: Little Rock State: AR Zip Code: 72204, 2139 DUNS Number: 787839448 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $12,900

Subrecipient or Contractor Name: CRISIS INTERVENTION CENTER City: Fort Smith State: AR Zip Code: 72901, 8483 DUNS Number: 164587321 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $16,400

Subrecipient or Contractor Name: GRANT COUNTY UNIFIED COMMUNITY RESOURCE COUNCIL City: Sheridan State: AR Zip Code: 72150, 0323 DUNS Number: 137055021 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $2,4600

Subrecipient or Contractor Name: GYST HOUSE City: Little Rock State: AR Zip Code: 72209, 4665 DUNS Number: 941775298 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $25,400

Subrecipient or Contractor Name: OUACHITA CHILDREN'S CENTER City: Hot Springs State: AR Zip Code: 71902, 1180 DUNS Number: 096677190 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $35,660

Subrecipient or Contractor Name: OUR HOUSE, INC. City: Little Rock State: AR Zip Code: 72206, 2304 DUNS Number: 802964403 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $41,400

Subrecipient or Contractor Name: RIVER CITY MINISTRY OF PULASKI COUNTY City: North Little Rock State: AR Zip Code: 72114, 5853 DUNS Number: 843604836 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $23,6400

Subrecipient or Contractor Name: RIVER VALLEY SHELTER FOR BATTERED WOMEN AND CHILDREN City: Russellville State: AR Zip Code: 72811, 2066 DUNS Number: 099684933 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $21,300

Subrecipient or Contractor Name: FAMILIES IN TRANSITION City: West Memphis State: AR Zip Code: 72303, 0015 DUNS Number: 098555860 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $22,200

Subrecipient or Contractor Name: THE SALVATION ARMY-EL DORADO City: El Dorado State: AR Zip Code: 71730, 6225 DUNS Number: 124154662 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $43,500

Subrecipient or Contractor Name: THE SALVATION ARMY-FAYETTEVILLE City: Fayetteville State: AR Zip Code: 72702, 4275 DUNS Number: 124161543 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $31,400

Subrecipient or Contractor Name: THE SALVATION ARMY-JONESBORO City: Jonesboro State: AR Zip Code: 72401, 3016 DUNS Number: 073511404 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $43,900

Subrecipient or Contractor Name: THE SALVATION ARMY-LITTLE ROCK City: Little Rock State: AR Zip Code: 72201, 1216 DUNS Number: 054297289 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $21,400

Subrecipient or Contractor Name: SAMARITAN OUTREACH City: Dardanelle State: AR Zip Code: 72834, 0183 DUNS Number: 800039328 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $29,400

Subrecipient or Contractor Name: THE SAFE PLACE City: Morrilton State: AR Zip Code: 72110, 0364 DUNS Number: 130084627 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $35,530

Subrecipient or Contractor Name: WOMEN AND CHILDREN FIRST City: Little Rock State: AR Zip Code: 72203, 1954 DUNS Number: 073953247 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $52,200

Subrecipient or Contractor Name: Harrison House of Hope City: Harrison State: AR Zip Code: 72601, 4442 DUNS Number: 040234211 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $49,700

Subrecipient or Contractor Name: Little Rock Community Mental Health Center City: Little Rock State: AR Zip Code: 72225, 0337 DUNS Number: 939924759 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $18,400

Subrecipient or Contractor Name: Arkansas River Valley Area Council City: Dardanelle State: AR Zip Code: 72834, 3400 DUNS Number: 075642140 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $301,400

Subrecipient or Contractor Name: Mississippi County Union Mission City: Blytheville State: AR Zip Code: 72316, 0501 DUNS Number: 081341091 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $51,900

Subrecipient or Contractor Name: Peace at Home Family Shelter City: Fayetteville State: AR Zip Code: 72703, 0051 DUNS Number: 029494593 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $17,900

Subrecipient or Contractor Name: Mission Outreach of Northeast Arkansas City: Paragould State: AR Zip Code: 72451, 1122 DUNS Number: 167584473 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $26,900

Subrecipient or Contractor Name: Margie's Haven House City: Heber Springs State: AR Zip Code: 72543, 0954 DUNS Number: 019427066 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $13,250

Subrecipient or Contractor Name: Genesis House City: Siloam Springs State: AR Zip Code: 72761, 1506 DUNS Number: 098576858 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $72,000

Subrecipient or Contractor Name: CASA Women's Shelter City: Pine Bluff State: AR Zip Code: 71611, 6705 DUNS Number: 176089063 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $66,360

Subrecipient or Contractor Name: Hope In Action City: Hope State: AR Zip Code: 71802, 0596 DUNS Number: 199532540 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $21,400

Subrecipient or Contractor Name: Options, Inc. City: Monticello State: AR Zip Code: 71657, 0554 DUNS Number: 625546544 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $62,260

Subrecipient or Contractor Name: Reclamation House City: Jonesboro State: AR Zip Code: 72401, 2780 DUNS Number: 080215038 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $17,400

Subrecipient or Contractor Name: Grace Christian College dba Stepping Stone Sanctuary City: Trumann State: AR Zip Code: 72472, 2111 DUNS Number: 048254911 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $16,400

Subrecipient or Contractor Name: Northwest Arkansas Women's Shelter City: Rogers State: AR Zip Code: 72757, 1059 DUNS Number: 959248816 Is subrecipient a victim services provider: Y Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $46,400

Subrecipient or Contractor Name: Riverview Hope Campus City: Fort Smith State: AR Zip Code: 72901, 4316 DUNS Number: 080664090 Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: $31,400

## CR-65 - Persons Assisted

4. Persons Served

4a. Complete for Homelessness Prevention Activities

| Number of Persons in Households | Total |
| --- | --- |
| Adults |  |
| Children |  |
| Don't Know/Refused/Other |  |
| Missing Information |  |
| Total |  |

Table 16 – Household Information for Homeless Prevention Activities

4b. Complete for Rapid Re-Housing Activities

| Number of Persons in Households | Total |
| --- | --- |
| Adults |  |
| Children |  |
| Don't Know/Refused/Other |  |
| Missing Information |  |
| Total |  |

Table 17 – Household Information for Rapid Re-Housing Activities

4c. Complete for Shelter

| Number of Persons in Households | Total |
| --- | --- |
| Adults |  |
| Children |  |
| Don't Know/Refused/Other |  |
| Missing Information |  |
| Total |  |

Table 18 – Shelter Information

4d. Street Outreach

| Number of Persons in Households | Total |
| --- | --- |
| Adults |  |
| Children |  |
| Don't Know/Refused/Other |  |
| Missing Information |  |
| Total |  |

Table 19 – Household Information for Street Outreach

4e. Totals for all Persons Served with ESG

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 18,184 |
| Children | 2,907 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 21,091 |

Table 20 – Household Information for Persons Served with ESG

5. Gender—Complete for All Activities

|  | Total |
| --- | --- |
| Male | 9,941 |
| Female | 8,207 |
| Transgender | 6 |
| Don't Know/Refused/Other | 5 |
| Missing Information | 25 |
| Total | 18,184 |

Table 21 – Gender Information

6. Age—Complete for All Activities

|  | Total |
| --- | --- |
| Under 18 | 2,907 |
| 18-24 | 1,422 |
| 25 and over | 1,640 |
| Don't Know/Refused/Other | 66 |
| Missing Information | 376 |
| Total | 6,411 |

Table 22 – Age Information

7. Special Populations Served—Complete for All Activities

Number of Persons in Households

| Subpopulation | Total | Total Persons Served – Prevention | Total Persons Served – RRH | Total Persons Served in Emergency Shelters |
| --- | --- | --- | --- | --- |
| Veterans | 0 | 0 | 0 | 0 |
| Victims of Domestic Violence | 0 | 0 | 0 | 0 |
| Elderly | 0 | 0 | 0 | 0 |
| HIV/AIDS | 0 | 0 | 0 | 0 |
| Chronically Homeless | 0 | 0 | 0 | 0 |

| Persons with Disabilities: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Severely Mentally Ill | 0 | 0 | 0 | 0 |
| Chronic Substance Abuse | 0 | 0 | 0 | 0 |
| Other Disability | 0 | 0 | 0 | 0 |
| Total (Unduplicated if possible) | 0 | 0 | 0 | 0 |

Table 23 – Special Population Served

## CR-70 – ESG 91.520(g) - Assistance Provided and Outcomes

10.  Shelter Utilization

| Number of New Units - Rehabbed | 0 |
| --- | --- |
| Number of New Units - Conversion | 0 |
| Total Number of bed-nights available | 0 |
| Total Number of bed-nights provided | 2,753 |
| Capacity Utilization | 0% |

Table 24	 – Shelter Capacity

11.  Project Outcomes Data measured under the performance standards developed in consultation with the CoC(s)

N/A

## CR-75 – Expenditures

11. Expenditures

11a. ESG Expenditures for Homelessness Prevention

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2016 | 2017 | 2018 |
| Expenditures for Rental Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation and Stabilization Services - Financial Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation & Stabilization Services - Services | 0 | 0 | 0 |
| Expenditures for Homeless Prevention under Emergency Shelter Grants Program | 245,713 | 176,390 | 326,237 |
| Subtotal Homelessness Prevention | 245,713 | 176,390 | 236,237 |

Table 25 – ESG Expenditures for Homelessness Prevention

11b. ESG Expenditures for Rapid Re-Housing

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2016 | 2017 | 2018 |
| Expenditures for Rental Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation and Stabilization Services - Financial Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation & Stabilization Services - Services | 0 | 0 | 0 |
| Expenditures for Homeless Assistance under Emergency Shelter Grants Program | 608,043 | 339,153 | 837,356 |
| Subtotal Rapid Re-Housing | 608,043 | 339,153 | 837,356 |

Table 26 – ESG Expenditures for Rapid Re-Housing

11c. ESG Expenditures for Emergency Shelter

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2016 | 2017 | 2018 |
| Essential Services | 0 | 0 | 0 |
| Operations | 941,424 | 896,102 | 899,620 |
| Renovation | 0 | 0 | 0 |
| Major Rehab | 0 | 0 | 0 |
| Conversion | 0 | 0 | 0 |
| Subtotal | 941,424 | 896,102 | 899,620 |

Table 27 – ESG Expenditures for Emergency Shelter

11d. Other Grant Expenditures

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2016 | 2017 | 2018 |
| Street Outreach | 7,859 | 8,007 | 6,873 |
| HMIS | 23,628 | 26,392 | 30,588 |
| Administration | 133,881 | 78,245 | 139,608 |

Table 28 - Other Grant Expenditures

11e. Total ESG Grant Funds

| Total ESG Funds Expended | 2016 | 2017 | 2018 |
| --- | --- | --- | --- |
| 3,484,837 | 1,960,548 | 1,524,289 | 2,240,282 |

Table 29 - Total ESG Funds Expended

11f. Match Source

|  | 2016 | 2017 | 2018 |
| --- | --- | --- | --- |
| Other Non-ESG HUD Funds | 0 | 0 | 0 |
| Other Federal Funds | 0 | 0 | 0 |
| State Government | 0 | 0 | 0 |
| Local Government | 0 | 0 | 0 |
| Private Funds | 0 | 0 | 0 |
| Other | 2,081,178 | 2,383,028 | 0 |
| Fees | 0 | 0 | 0 |
| Program Income | 0 | 0 | 0 |
| Total Match Amount | 2,081,178 | 2,383,028 | 0 |

Table 30 - Other Funds Expended on Eligible ESG Activities

11g. Total

| Total Amount of Funds Expended on ESG Activities | 2016 | 2017 | 2018 |
| --- | --- | --- | --- |
| 7,949,043 | 4,041,726 | 3,907,317 | 2,240,282 |

Table 31 - Total Amount of Funds Expended on ESG Activities

Attachments

Attachment 1

PR28 PER Financial Summary

This page left blank intentionally.

Attachment 2

PR28 PER Financial Summary

This page left blank intentionally.

Attachment 3

IDIS Matrix Codes

This page left blank intentionally.

Attachment 3:  List of IDIS Matrix Codes

| Matrix Code | Eligible Activity (State and Entitlement CDBG) |
| --- | --- |
| 01 | Acquisition of Property - 570.201(a) |
| 02 | Disposition - 570.201(b) |
| 03 | Public Fac. & Impvm'ts - 570.201(c) |
| 03A | Senior Centers |
| 03B | Handicapped Centers |
| 03C | Homeless Facilities (not operating costs) |
| 03D | Youth Centers |
| 03E | Neighborhood Facilities |
| 03F | Parks, Recreational Facilities |
| 03G | Parking Facilities |
| 03H | Solid Waste Disposal Improvements |
| 03I | Flood Drainage Improvements |
| 03J | Water/Sewer Improvements |
| 03K | Street Improvements |
| 03L | Sidewalks |
| 03M | Child Care Centers |
| 03N | Tree Planting |
| 03O | Fire Station/Equipment |
| 03P | Health Facilities |
| 03Q | Abused and Neglected Children Facilities |
| 03R | Asbestos Removal |
| 03S | Facilities for AIDS Patients (no op'ting costs) |
| 04 | Clearance, Demo, Remediate - 570.201(d) |
| 04A | Cleanup of Contaminated Sites |
| 05 | Public Services - 570.201(e) |
| 03T | Operating Costs Homeless/AIDS Patients |
| 05A | Senior Services |
| 05B | Handicapped Services |
| 05C | Legal Services |
| 05D | Youth Services |
| 05E | Transportation Services |
| 05F | Substance Abuse Services |
| 05G | Battered and Abused Spouses |
| 05H | Employment Training |
| 05I | Crime Awareness |
| 05J | Fair Housing Activities - Subject to Public Service Cap |
| 05K | Tenant/Landlord Counseling |

| 05L | Child Care Services |
| --- | --- |
| 05M | Health Services |
| 05N | Abused and Neglected Children |
| 05O | Mental Health Services |
| 05P | Screening for Lead Based Paint/Lead Hazards |
| 05Q | Subsistence Payments - 570.207(b)(4) |
| 05R | Homeownership Assistance (not direct) |
| 05S | Rental Housing Subsidies |
| 05T | Security Deposits |
| 05U | Housing Counseling |
| 05V | Neighborhood Cleanups |
| 05W | Food Banks |
| 06 | Interim Assistance - 570.201(f) |
| 07 | Urban Renewal Completion - 570.201(h) |
| 08 | Relocation - 570.201(i) |
| 09 | Rental Income Loss - 570.201(j) |
| 11 | Privately Owned Utilities - 570.201(l) |
| 12 | Construction of Housing - 570.201(m) |
| 13 | Homeownership Direct - 570.201(n) |
| 14A | Rehab; Single-Unit Res. - 570.202 |
| 14B | Rehab; Multi-Unit Residential |
| 14C | Public Housing Modernization |
| 14D | Rehab; Other than Public-Owned Residential Blds |
| 14E | Rehab. Pub./Pvt.-Comm'/Indust' - 570.202(a)(3) |
| 14F | Energy Efficiency Improvements |
| 14G | Acquisition for Rehabilitation |
| 14H | Rehabilitation Administration - 570.202(b)(9) |
| 14I | Lead-Based Paint Abtm't - 570.202(f) |
| 14J | Housing Svc's - HOME Prog. - 570.201(k) |
| 15 | Code Enforcement - 570.202(c) |
| 16A | Residential Historic Preservation |
| 16B | Non-Residential Historic Preservation |
| 17A | ED Acquisition by Recipient - 570.203(a) |
| 17B | CI Infrastructure Development |
| 17C | CI Building Acq., Construction, Rehabilitation |
| 17D | Other Commercial/Industrial Improvements |
| 18A | ED Assistance to For-Profits - 570.203(b) |
| 18B | ED Administration & TA - 570.203(c) |
| 18C | Micro-Enterprise Assist. - 570.201(o) |
| 19C | Nonprofit Capacity Building - 570.201(p) |
| 19D | Assist. Higher Educ. Inst. - 570.201(q) |
| 19E | Operation and Repair of Foreclosed Property |
| 19F | Planned Repayments of Sec.108 Loans |
| 19G | Unplanned Repayments of Sec.108 Loans |
| 19H | State CDBG Technical Assistance to Grantees |
| 20 | Planning-Ent. Com'ties - 570.205 |
| 20A | State Planning |
| 21A | General Program Admin. - 570.206 |
| 21B | Indirect Costs |
| 21C | Public Information |
| 21D | Fair Housing Activity (subject to Admin. cap) |
| 21E | Submissions or Applications for Federal Programs |
| 21H | CDBG Funding of HOME Admin. |
| 21I | CDBG Funding of HOME CHDO Operating Costs |
| 21J | State Administration Costs |
| 22 | Unprogrammed Funds |
| 23 | Tornado Shelters - Private Mobile H Parks |
| 24A | Payment of interest on Section 108 loans |
| 24B | Payment of costs of Section 108 financing |
| 24C | Debt service reserve - Section 108 |

This page left blank intentionally.

Attachment 4

PER Review Checklist

This page left blank intentionally.

Attachment 4:  PER Review Checklist

A. General Information Review

- Did the state submit its report within 90 days after the close of its program year?

Yes / No

- If no to question 1, what was the state's reason for missing the submission date?

Enter the actual date of the submission

- Is there a PR28 Financial Summary for each open grant?

Yes / No

- Are any parameter adjustments (PR28 Financial Summary) explained in an attachment?

Yes / No

- Do the attached explanations sufficiently explain the adjustments?

Yes / No

- Is the PR28 Financial Summary internally consistent? Refer to Attachment 1 to for the various lines that have a mathematic relationship to one another.

Yes / No

- Is the timeframe selected for meeting the principal benefit test (Line 63) consistent with the period specified in the state's Consolidated Plan certification and with §570.484(a)? Yes / No

B. Financial Review

Review each allocation to determine if the financial information on the allocation is correct. Use the space provided to respond to any negative answers.

- Are the grant allocation, program income and any Section 108 funds properly reported in Section A?

Yes / No

- Is Line 11 consistent with the HUD 40108 submitted for the same allocation, demonstrating compliance with the 15-month deadline pursuant to §570.494? Keep in mind that it is reasonable to see some variance between Line 11 and the HUD 40108 report of amounts “obligated and announced.” For instance, the 15-month deadline and the timing of this report may not align. Additionally, certain awards may have been subsequently de-obligated by the state, which would reasonably cause Line 11 to be less than the reported amount on the HUD 40108.

Yes / No

- Did the state report an appropriate state administration match? This is a manual entry on Report Parameter screen, for which an explanation must be attached. This is the only place in IDIS to enter the amount of the administration cost match required by 24 CFR 570.489(a)(1). Is Line 18 ≥ (Line 31 minus 100,000.00)?

Yes / No

- Did the state report compliance with the state administration cap pursuant to 24 CFR 570.489(a)(1)(i)? State administration expenditures cannot exceed 3 percent plus 100,000.

State Administration Cap*: (Line 31)≤((Line 1+Line 5)*0.03)+100,000.

Yes / No

- Did the state report compliance with the state technical assistance cap pursuant to 24 CFR 570.489(a)(1)(ii)? State technical expenditures cannot exceed 3 percent.

State Technical Assistance Cap: (Line 34)≤((Line 1+Line 5)*0.03)

Yes / No

- Did the state report compliance with the state administration & technical assistance cap pursuant to 24 CFR 570.489(a)(1)(iii)?

Combined State Admin* and TA Cap:

((Line 31-100,000.00)+Line 34)≤ ((Line 1+Line 5)*0.03)

Yes / No

*For questions 11 and 13, under the 2014 and prior grants, pursuant to

§570.489(a)(1)(v), states had the option of demonstrating compliance with this requirement in two ways, either cumulatively or year-by-year. Pursuant to the regulatory changes made by the Interim Rule, FR 5797-I-01, Changes to Accounting Requirements for the Community Development Block Grants (CDBG) Program, for 2015 and subsequent grants, compliance with §570.489(a)(1) may only be demonstrated on a year-by-year basis.

- Did the state report compliance with the public service cap pursuant to HCDA § 105(a)(8)? Is Line 49 ≤ 15 percent?

Yes / No

- Did the state report compliance with the 20 percent combined planning and administration cost cap pursuant to 24 CFR 570.489(a)(3)(ii)? Is Line 58 ≤ 20 percent? Yes / No

- Did the state report compliance with the 20 percent cap on the annual grant for planning and administration costs pursuant to §570.489(a)(3)(iii)? Is Line 62 ≤ 20 percent?

Yes / No

- Did the state report compliance with the Low and Moderate Income Benefit test?

Is Line 77 ≥ 70 percent? Keep in mind that this percentage might be less than 70 percent

at various points in the life of the grant(s) involved. Full compliance is determined when

the grant(s) are fully expended.

Yes / No

(Refer to Chapter 4 of the CPD Monitoring Handbook 6509.2, Exhibit 4-3, for more information on calculating the state's percentage in meeting the principal benefit test. See: https://www.hudexchange.info/resource/290/hud-community-planning-and-development- monitoring-handbook-65092-rev6/ )

This page left blank intentionally.

Attachment 5

HOME

- Racial Ethnic Data

- CR50 Unit Inspections

- Consolidated Plan County Designations

This page left blank intentionally.

HOME - Racial Ethnic Data

HOME - Racial Ethnic Data

CR5-50 Unit Inspections

CR5-50 Unit Inspections

CR5-50 Unit Inspections

CR5-50 Unit Inspections

County Designations

County Designations